## Current Project List
E&O Project list
Last edited 1/27/11 by SM
Project Type | Project | Who | Short term (0-6 mo) (Jan. '11 - Jun. '11) | Mid-range (6-12 mo) (Jul. '11 - Dec. '11) | Long-term (12+ mo) (Jan. '12 on)
Exhibits
| PTMSC- seasonal drivers of Temp, Sal., DO, and Chl | Sarah | Design/development | Evaluation and modification
| Other locations- PTMSC exhibit modified for new locations | Sarah | Look for grant opps. | Submit grant proposals | Modify for other places
| General NANOOS- what is NANOOS? | Unkwn |  |  | Initial concepts
Theme pages
| Ocean Acidification | A&S |  | Improve | Evaluate with users?
| Hypoxia | Sarah |  | Finish animation revisions | Evaluate with users?
| Coastal Hazards (contact: Jon Allan) | Sarah | Compile info and create content | Development by Troy | Evaluate with users?
| HABs (contact: Jan Newton) | Amy | Compile info and create content, development by Troy |  | Evaluate with users?
| Climate (contact: Jan Newton and Jon Allan) | Sarah | create front page, discussions of content | create content, Development by Troy
| Coastal and Marine Spatial Planning (contact: Emilio Mayorga) | Sarah | create front page, discussions of content | create content, Development by Troy
| Fisheries (contact: Dan Hannafious) | Sarah | create front page, discussions of content | create content, Development by Troy
| Marine Ops (contact: David Jones) | Amy | create front page, discussions of content | create content, Development by Troy
| Ecosystem Assesment (contact: Jan Newton) | Amy | create front page
Outreach Events/Workshops
| Storming the Sound (Puget Sound Partnership) | Amy | Jan 27 - North (sending materials, La Connor, WA); Mar 25 - Central (presenting, Seattle, WA) | Fall - West, South (send materials) | North, South, Central, West
| Science and Math Investigatory Learning Experiences (SMILE) | A&S | Jan 28 - teacher workshop; Apr 15 - H. Sch. Challenge (Corvallis, OR)
| Facilitating Boat Based Education (WA Sea Grant, COSEE-OLC) | Amy | February 28
| Seattle Bay Watershed Education Training (BWET) (NOAA) | Amy | March 13 (hosting) (Seattle, WA)
| Enviro. Ed. Asso. Of WA/WA Science Teachers Asso. | Amy | Mar 18-20 (exhibit, possible presentation, Poulsbo, WA)
| Saltwater Sportsmen's Show | Sarah | Mar 19 (booth) (Salem, OR)
| NW Biology Instructors Organization Conference (NWBIO) | Amy | Apr 29-30 (exhibit? Presentation? Yakima, WA)
| Hatfield SeaFest | Sarah | End of Jun? (Newport, OR)
| Northwest Aquatic and Marine Educators (NAME) Conference | A&S | planning | Jul 12-16 (presenting, Port Angeles, WA) | NAME/NMEA (AK)
| National Marine Educators Association (NMEA) Conference |  |  | Jun 28-Jul 3 (send materials, Boston, MA)
| Oregon Science Teachers Asso. Conference |  |  | Oct 14 (Coos Bay, OR)
| Salish Sea Ecosystem Conference |  |  | Oct 25-27 (Vancouver, BC)
| Heceta Head Coastal Conference | Sarah |  | Late Oct (Florence, OR)
| Coastal and Estuarine Research Reserve (CERF) Conference |  |  | Nov 6-10 (send materials, Daytona Beach, FL)
| National Science Teachers Asso. Conference |  |  | Dec 8-10 (Seattle, WA)
Classroom Resources
| Ocean acidification | Amy |  | work with Casey (NOAA NWFSC) - hopefully internal NOAA grant may be available, bring ed resources, PNW issues to theme page
| HABs | Amy |  | work with Casey (NWFSC)/ Liz Tobin (UW) update NWFSC "HAB Hunter" curriculum to incorporate RTD
| Puget Sound circulation | Amy |  | work with UW research group to make/find model visualization on PS circulation, test on OIP cruises, create content for web to go with PRISM dataset | Development by Troy for NANOOS web
Product testing/surveys/focus grous
| Tuna fisher page | Sarah | Tuna page with fishers focus group | Feedback reflected online
| Other user pages | A&S | Apr - Determine priority groups at Tri-committee meeting | Develop pages
| General user surveys | A&S | Hand out at outreach events | Compile survey results, diseminate
| NVS | A&S |  | Testing with priority groups
Marketing
| Web | A&S | Re-shuffle "About NANOOS" section |  | Update people page with extended profiles
| Outreach materials | A&S | Redesign brochure
Newsletter
|  | A&S | Jan - 2011 winter edition; May - 2011 Spring edition | Sept - 2011 Fall edition | Jan - 2012 Winter edition; May - 2012 Spring Edition; Sept - 2012 Fall edition
Citizen Science
|  | A&S | find possible grant opps | submit grant | submit grant

## Completed Projects & Events
Completed Projects/Events
Last edited by SM 12/17/10
Project Type | Project | Who | Date | Number Served | Contact hours | Review
Exhibits
Theme pages
Workshops
| Storming the Sound | Amy | West | 12-15 educators attended talk; 75 at event; 20 signed up for newsletter | 15 hours (12 at hour session, plus visits to table) | brought NANOOS tabletop exhibit, should do so again; educators interested in WA coast issues i.e. buoy/glider - next STSW presentation should be on that; after event met with OPI staff (Adrian Sherlock) to discuss possible water quality data collection by OPI; follow-up on Adrian's part after he talks with staff
| Tacoma BWET | Amy | Nov 6/7 | 30 educators attended | 30 hours (some time on boat on Saturday, then 45 minutes to whole group on Sunday) | Day 1 - became on OIP cruise w/ two 3 hr cruises with 15 teachers each. OIP stations: CTD, Water quality, plankton, microplastics (Julie Masura), navigation/wheelhouse; the other half of the teachers were on land with SEA/LEAF School. Day 2 - 30-45 minute presentations by many community members including Puyallup timber manager, Tacoma public utilities (stormwater) - we traced die into drain and out into waterway, UWT Peter Selkin - presented lesson on Google Earth historical aerial photos of WA, hyrology lesson (URL in email); PEI about landscape investigations curriculum. I spoke about NANOOS and showed NVS, would have been better to combine the NANOOS presentation with Day 1 activities. Attendees - many worked with younger students, many had hard time w/ laptops, google earth - had never used it
| Hood Canal BWET | Amy | Nov 13/14 | 8 educators attended | 48 hours | Attended Day 1 onboard Indigo. I ended up doing a CTD rotation with Renee and Meredith from HCSEG, Lori Hanson & Audrey - OIP volunteers - did OIP water quality. At CTD station tied it into NANOOS and ocean observing. I had NVS and HCDOP data from buoys, presented the data in conjunction with HC hypoxia "recipe" ppt. Funny dynamics with the 2 different rotations of teachers, one group very engaged, lots of questions and discssion. One group w/ a teacher convinced middle schoolers wouldn't be able to read graphs.
| Pacific Education Institute/Olympic Coast National Marine Sanctuary/NANOOS | Amy | Nov 5 planning | Jacqueline (OCNMS), PEI, Grays Harbor College Americorps members | N/A | met in Olympia for half day meeting, not sure what will come of the meeting. One day ocean literacy workshop for 20 educators in January led by 2 Americorps members - may include NANOOS resources in webquest. Potential to work w/ PEI to build curric. similar to Landscape Investigations but focused on coastal communities and connection to ocean, ties into data coming from buoys etc. What are the observations students could make in their schoolyard/local beach that would relate to ocean conditions (i.e wind, speed, direction, beach slope...
Classroom Resources
User testing/surveys
Marketing
| Update People page with basic info | Sarah | Fall 2010 | N/A | N/A
| Update People page with pictures | Sarah | Fall 2010 | N/A | N/A
Newsletter
Citizen Science
Outreach events
| Pacific Marine Expo | Amy |  | ? - about 200 NANOOS stickers taken | 4 hours | Had materials at WA Sea Grant/AK Sea Grant booth. Many of the fishermen attending had boats in Seattle but fish up in Alaska. Audience definitely commercial fishermen. If they are a target group for us, then we should work with AOOS to have a booth together at future conference.
| Heceta Head Conference | Sarah | 2010-10-29 | Talked to about 20 local resource managers and city employees | 12 hours | Had materials (newsletters, stickers, pens) and a laptop showing NVS at booth. Many attendees were OR coast residents, city employees, resource managers, or local politians. Most conversations were educating people about what NANOOS is and the data we collect.

## Upcoming Outreach Events
Upcoming Outreach Events
Last edited by SM 12/17/10
NANOOS/IOOS | Targeted Group | Event | Location | DATES | Abstracts due | Exhibtor booth cost | Exhibitor deadline | Website
NANOOS | educators | SMILE | Corvallis | 2010-01-28
IOOS? |  | Seafood Summit | Vancouver BC | 1/31/2011-2/2/2011
NANOOS | fishers | Salty Dog | Newport | TBD early March 2011
NANOOS | educators | Washington Science Teachers Association/EEAW joint conference | Seattle | 3/13/2011-3/16/2011 | past | $310 (full)/$110 (non profit auxiliary space) |  | http://eeaw.org/conference/2011-eeaw-wsta-joint-conference/exhibitor-and-sponsor-information/
NANOOS | educators | Storming the Sound Central | Seattle | 2011-03-25
NANOOS | c.c. educators | NWBIO | Yakima | 4/29/2011-4/30/2011 | 2011-03-30
IOOS? |  | International Oil Spill | Portland | 5/23/2011-5/26/2011
IOOS? | educators | NMEA Conference | Boston | 6/29/2011-7/3/2011 | 2011-02-18
NANOOS | educators | NAME | Port Angeles | 7/13/2011-7/16/2011
IOOS? | scientists/resource managers | American Fisheries Society | Seattle | 9/4/2011-9/8/2011
NANOOS | scientists/resource managers | Puget Sound Geargia Basin | Seattle or BC | TBD fall 2011
IOOS? | educators | NSTA regional conference | Seattle | 12/8/2011-12/10/2011 |  | 1525