

**NANOOS Next 5-Year Effort: 2020 Timeline**

For any questions, please contact NANOOS Program Manager, Nick Rome (nrome@uw.edu).

|  |  |  |
| --- | --- | --- |
| **DATE** | **ACTION** | **POINT** |
| 25 June | Expressions of Interest (EOI) process announced | PIs |
| 25 July | All EOIs due to janewton@uw.edu and nrome@uw.edu  | PIs |
| Early August  | EOIs prioritized by NANOOS Governing Council Executive Committee | GC Exec Comm |
| Late August | Further Management deliberation with NANOOS Governing Council Executive Committee to finalize budget and proposal scope | GC Exec Comm |
| 31 Aug  | All included PIs notified | PIs |
| Sept  | Proposal writing begins | NANOOS |
| 30 Sep | All sub-budgets due to their respective institutional fiscal offices | PIs |
| 30 Oct | All sub-budgets, SOW, budget justification due to APL-UW | PIs |
| 30 Nov | Proposal submission target date | NANOOS |